## Instructions
IT 3310 · Week 8 Project Schedule Template · Supporting Excel Artifact
NovaTech Consulting · RCHN Intake & Scheduling System Replacement
HOW TO USE THIS TEMPLATE
This workbook has two sheets: Instructions (this page) and Project Schedule (your work).
Use this workbook to expand your RCHN project schedule. The five-phase sample is illustrative; your interactive assignment uses four WBS groupings and a separate four-activity exercise.
Keep the provided column headers, dropdowns, conditional formatting, and formulas. Do not type in formula-driven cells.
Save your completed workbook as an Excel file (.xlsx) and include it in your Week 8 portfolio according to Blackboard instructions.
The GitHub markdown (.md) link in the interactive assignment is a separate requirement. An Excel file is not a .md file.
COLUMN GUIDE · What to enter in each column
WBS Code | The hierarchical number for this task (e.g. 1.0, 1.1, 1.2). Phase rows use whole numbers. Tasks under each phase use decimals.
Task Name | A short, specific description of the work. Use action language. Example: Configure intake workflow for Clinic 1. Not: Work on system.
Phase | Which major phase this task belongs to: Initiation, Planning, Development, Deployment, or Closure.
Task Type | Choose from the dropdown: Phase Header, Task, or Milestone. Milestone rows will highlight automatically in gold.
Predecessor | Enter the predecessor WBS code (such as 3.1). The A–D IDs in the interactive activity are simplified examples; they are not WBS codes. Multiple predecessors can be described in Notes.
Dependency Type | Choose from the dropdown: FS (Finish-to-Start), SS (Start-to-Start), FF (Finish-to-Finish), or SF (Start-to-Finish). Select the relationship that best reflects the work.
Start Week | Project timeline week number, not the course week. Whole numbers only. With week-level planning, exact day-level dependencies are approximate.
End Week | The project week when this task ends. It must be equal to or greater than Start Week.
Duration | Automatically calculated as inclusive elapsed weeks for tasks; milestones display 0. A week is not the same unit as the working-day durations in the interactive assignment.
Critical Path | Enter YES only after analyzing the dependent sequence and float. This field is a manual judgment, not an automatically calculated critical path.
Notes | Optional. Add context, constraints, risks, or dependency details that help explain the schedule decision.
COLOR CODING GUIDE
Sample | Phase Header rows (automatically applied when Task Type = Phase Header)
Sample | Critical Path tasks (automatically applied when Critical Path = YES)
Sample | Milestone rows (automatically applied when Task Type = Milestone)
Sample | Regular task rows (default for all Task rows)
Sample | Empty or unused rows
TIPS FOR STUDENTS NEW TO EXCEL
1. To move between cells, press Tab to go right or Enter to go down.
2. To edit a cell you already filled in, click on it and press F2, or just start typing to replace it.
4. Do not type in Duration (column I). Tasks use inclusive project weeks; milestones have zero duration.
4. Do not type in the Duration column (column I). It calculates automatically from Start Week and End Week.
5. If a cell shows ##### it means the column is too narrow to display the value. Drag the column edge to make it wider.
6. To save your work, press Ctrl+S (Windows) or Cmd+S (Mac). Save often.
7. When you are done, use File > Save As and make sure the file type is Excel Workbook (.xlsx).
8. Save the completed .xlsx in your Week 8 portfolio; use a separate GitHub .md link when submitting the interactive assignment.

## Project Schedule
IT 3310 ¦ Week 8 Project Schedule ¦ David Zupinski ¦ RCHN ¦ Proposed timeline
WBS Code | Task Name | Phase | Task Type | Predecessor | Dependency Type | Start Week | End Week | Duration (weeks) (auto; milestones = 0) | Critical Path (YES/blank) | Notes
1.0 | PLANNING AND SCOPE BASELINE | Planning | Phase Header | [6 empty] | David Zupinski. Proposed scope based on Week 5 scenario and saved Week 7 backlog. Sponsor approval pending.
1.1 | Confirm shared intake, identity and access rules | Planning | Task |  |  | 1 | 1 | 1 | YES | Activity A: 5 working days. Confirm required fields, patient identity and authorized roles with clinic representatives.
1.2 | Document constraints and acceptance plan | Planning | Task | 1.1 | SS (Start-to-Start) | 1 | 1 | 1 | YES | Parallel planning with assigned analyst. Both 1.1 and 1.2 must finish before approval. Same one-week duration.
1.3 | Scope and delivery baseline approved | Planning | Milestone | 1.1 | FS (Finish-to-Start) | 1 | 1 | 0 |  | End of Week 1, after 1.1 AND 1.2. Sponsor approval recorded; targets below remain estimates until this event.
2.0 | INTAKE AND SCHEDULING SOLUTION | Development | Phase Header | [6 empty] | Stories 1-5. Story 6 patient portal is deferred. Billing integration, dashboard and mobile app require a separate scope decision.
2.1 | Configure intake and retained-data workflow | Development | Task | 1.3 | FS (Finish-to-Start) | 2 | 3 | 2 | YES | Activity B: 10 working days. Stories 1,4,5 include same-patient retention, access controls and corrective field guidance.
2.2 | Configure clinic/date availability | Development | Task | 1.3 | FS (Finish-to-Start) | 2 | 2 | 1 |  | Activity C: 5 working days; one week of float before 2.3. Includes explicit empty and load-error states. Separate specialist assumed.
2.3.1 | Integrate booking and test conflict handling | Development | Task | 2.1 | FS (Finish-to-Start) | 4 | 5 | 2 | YES | Activity D: 10 working days. Requires BOTH 2.1 and 2.2. Verify one booking per slot and truthful success/failure results.
2.3.2 | Run cross-clinic acceptance tests | Development | Task | 2.3.1 | FS (Finish-to-Start) | 6 | 6 | 1 | YES | Designated RCHN representatives execute acceptance cases across all six clinic configurations. Resolve release-blocking defects.
2.3.3 | Core solution accepted for pilot | Development | Milestone | 2.3.2 | FS (Finish-to-Start) | 6 | 6 | 0 |  | End Week 6. Signed UAT record, required-field consistency, authorized retention, availability and concurrent-booking tests passed.
3.0 | CLINIC READINESS AND ROLLOUT | Deployment | Phase Header | [6 empty] | Staff training covers all six clinics. Pilot and observation are proposed delivery assumptions, not prior approved commitments.
3.1.1 | Prepare role-based training materials | Deployment | Task | 2.3.1 | SS (Start-to-Start) | 4 | 5 | 2 |  | Can start with integration using stable workflows. Five days float through Week 6 before pilot training; update after UAT.
3.1.2 | Train designated pilot-clinic staff | Deployment | Task | 2.3.3 | FS (Finish-to-Start) | 7 | 7 | 1 | YES | Also requires 3.1.1. Attendance and demonstrated intake-to-booking competency recorded before pilot launch.
3.2.1 | Pilot clinic launched | Deployment | Milestone | 3.1.2 | FS (Finish-to-Start) | 7 | 7 | 0 |  | End Week 7. Pilot smoke test, support contacts and rollback readiness accepted.
3.2.2 | Observe pilot and resolve rollout blockers | Deployment | Task | 3.2.1 | FS (Finish-to-Start) | 8 | 12 | 5 | YES | Five-week window = 35 calendar days, reserving at least 30 for observation. Review issues and approve wider rollout at end Week 12.
3.1.3 | Train staff at remaining five clinics | Deployment | Task | 3.2.1 | FS (Finish-to-Start) | 10 | 12 | 3 |  | Intentional two-week wait after pilot launch to incorporate early feedback. Three weeks training; can move to Weeks 8-10 if capacity permits.
3.3.1 | Deploy and verify remaining five clinics | Deployment | Task | 3.2.2 | FS (Finish-to-Start) | 13 | 13 | 1 | YES | Requires BOTH pilot review 3.2.2 and training 3.1.3. Perform intake-to-booking smoke test at each clinic.
3.3.2 | All six clinics live and verified | Deployment | Milestone | 3.3.1 | FS (Finish-to-Start) | 13 | 13 | 0 |  | End Week 13. Signed rollout checklist, training records, six clinic smoke tests and support/rollback arrangements documented.
4.0 | POST-LAUNCH SUPPORT AND HANDOFF | Closure | Phase Header | [6 empty] | Support covers the complete rollout. The support duration is a recommended Week 5 inclusion requiring approval.
4.1 | Provide 90-day rollout support | Closure | Task | 3.3.2 | FS (Finish-to-Start) | 14 | 26 | 13 | YES | 13 weeks = 91 calendar days. Track and resolve issues; confirm exact 90-day end date once calendar start is approved.
4.2 | Prepare operating guides and ownership transfer | Closure | Task | 4.1 | SS (Start-to-Start) | 25 | 26 | 2 |  | Planned late start to incorporate support findings. Two-week task has 11 weeks flexibility; named service owner accepts guides and open issues.
4.3.1 | Document lessons learned and closure evidence | Closure | Task | 4.1 | SS (Start-to-Start) | 25 | 26 | 2 |  | Parallel with handoff preparation. Review issues, decisions and lessons. Same planned window and float as 4.2.
4.3.2 | Final handoff and closure accepted | Closure | Milestone | 4.1 | FS (Finish-to-Start) | 26 | 26 | 0 |  | End Week 26 after 4.1,4.2 AND 4.3.1. Sponsor accepts handoff, service owner and disposition of remaining issues.
Total Tasks |  |  |  | 14
Total Milestones |  |  |  | 5
Critical Path Tasks |  |  |  | 9
Project Start Week |  |  |  | 1
Project End Week |  |  |  | 26
Latest End Week (check) |  |  |  | 26

## A-D Practice Bridge
Week 8 ¦ David Zupinski ¦ Four-activity RCHN subset
Activity ID | Example activity | Duration (working days) | Predecessor IDs | Earliest start week | What the predecessor means
A | Confirm shared intake, identity and access rules | 5 | None | 1 | Shared rules establish the intake and availability baseline.
B | Configure intake and retained-data workflow | 10 | A | 2 | Intake implementation waits for A.
C | Configure clinic/date availability | 5 | A | 2 | Availability can run parallel to B after A.
D | Integrate booking and verify conflict/error handling | 10 | B,C | 4 | Booking integration waits for BOTH intake and availability.
Practice assumptions
Five working days per project week. Finish-to-Start relationships. Start Week is the project timeline, not the course week.
Subset maps to Project Schedule codes 1.1, 2.1, 2.2 and 2.3.1. It ends in Week 5; full rollout and support continue through Week 26.
Independent exercise: A3-B4-D2 = 9 days; A3-C6-D2 = 11 days (critical). A two-day critical delay makes 13 days.
Interpretation
A WBS identifies project deliverables/work packages. Schedule activities are the actions needed to produce them. One work package can require several activities.

## Gantt View
RCHN Project Schedule · Week-by-Week View
■ Task span ◆ Milestone Blank = not scheduled. Week numbers refer to the project timeline.
WBS | Task / milestone | Type | Critical? | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
1.0 | PLANNING AND SCOPE BASELINE | Phase Header | 0
1.1 | Confirm shared intake, identity and access rules | Task | YES | bar: 1
1.2 | Document constraints and acceptance plan | Task | YES | bar: 1
1.3 | Scope and delivery baseline approved | Milestone | 0 | bar: 1
2.0 | INTAKE AND SCHEDULING SOLUTION | Phase Header | 0
2.1 | Configure intake and retained-data workflow | Task | YES | bar: 2 to 3
2.2 | Configure clinic/date availability | Task | 0 | bar: 2
2.3.1 | Integrate booking and test conflict handling | Task | YES | bar: 4 to 5
2.3.2 | Run cross-clinic acceptance tests | Task | YES | bar: 6
2.3.3 | Core solution accepted for pilot | Milestone | 0 | bar: 6
3.0 | CLINIC READINESS AND ROLLOUT | Phase Header | 0
3.1.1 | Prepare role-based training materials | Task | 0 | bar: 4 to 5
3.1.2 | Train designated pilot-clinic staff | Task | YES | bar: 7
3.2.1 | Pilot clinic launched | Milestone | 0 | bar: 7
3.2.2 | Observe pilot and resolve rollout blockers | Task | YES | bar: 8 to 12
3.1.3 | Train staff at remaining five clinics | Task | 0 | bar: 10 to 12
3.3.1 | Deploy and verify remaining five clinics | Task | YES | bar: 13
3.3.2 | All six clinics live and verified | Milestone | 0 | bar: 13
4.0 | POST-LAUNCH SUPPORT AND HANDOFF | Phase Header | 0
4.1 | Provide 90-day rollout support | Task | YES | bar: 14 to 26
4.2 | Prepare operating guides and ownership transfer | Task | 0 | bar: 25 to 26
4.3.1 | Document lessons learned and closure evidence | Task | 0 | bar: 25 to 26
4.3.2 | Final handoff and closure accepted | Milestone | 0 | bar: 26
0 | 0 | 0 | 0
0 | 0 | 0 | 0